## 07.12.2020 copy
Project contributors (past, present): | Task status color code: | Main contributors: | Other contributors:
Suliana Manley (SM) | Completed | Execute, direct involvement | Advise, brainstorm, etc.
Dora Mahecic (DM) | Ongoing
Juliette Griffié (JG) | Not yet started
Khalid Ibrahim (KI)
Willi Stepp (WS)
Hélène Perreten Lambert (HPL)
Florent Wenger (FW)
Martin Weigert (MW)
Aim | Task | Main contributor(s) | Other contributor(s) | Description | Comments
Supervision and management | Conceptualization | SM, DM | JG | Development of basic idea and storyline.
| Funding acquisition | SM |  | ?
| Supervision | SM, DM |  | SM overall supervision, DM training and integrating new project members.
| Project administration | SM, DM |  | Task distribution, keeping track of data, planning, taking care of this sheet, etc.
Smart acquisition framework | Preliminary iSIM hardware and software work | DM |  | Putting in place the hardware and software for iSIM operation. Software easily modifiable and user friendly.
| Develop framework for continuous and adjustable iSIM acquisition | DM |  | Modifying existing iSIM acquisition controls to allow for continuously adjustable iSIM acquisition. Conceptualization of how to best implement adjustable temporal resolution.
| Integrate event detection network into smart framework | WS | DM, MW, FW | Connect smart iSIM controls with the network by organising the data flow between MicroManager, MATLAB and the network python scripts. Conceptualization done by Willi & Dora, execution by Willi.
Event detection framework | Preliminary event detection | DM | SM | Calculate readout from acquired images on the fly (here using intensity of molecular marker), to adjust temporal resolution.
| Develop automatic labelling procedure | DM | JG, MW, KI | Identifying a method to automatically label mitochondrial constrictions. Conceptualized and implemented using Hessian filtering. Previous attempts by KI did not appear successful.
| Generate training dataset | DM |  | Large scale processing of data using Hessian filtering data labeling strategy and manually editing said dataset to create the optimal training dataset.
| Build and train neural network | DM | MW | Creating the neural network and training using labelled dataset.
| Characterize performance and optimize network parameters | DM |  | Optimizing network parameters and quantifying performance based on the probability map outputs.
Simulation platform | Develop simulation platform using synthetic data | DM | JG | Testing different strategies using simulated readouts and quantifying the benefit of ATS.
| Develop simulation platform using real data | WS | DM, JG | Adapting GUI to read frame based on metric computed from previously read frame. | Not crucial at this point and not sure it will address what I hope, but worth keeping in mind. I think the current GUI from Willi could be easily adapted for this purpose.
Application: mitochondrial division | Acquire adaptive data | DM, WS |  | Dora in charge of mitochondrial division, Willi shadowing
| Acquire non-adaptive data | DM |  | Data with constant frame rate: same as min and max used in ATS.
| Optimize decision parameters | DM, WS |  | Choosing trigger for adaptation response. Optimising behaviour to minimise noise and maximise event recognition. | Eventually might be useful to use simulation platform for this.
| Sample preparation | HPL, DM |  | Finding best labeling strategy. Producing samples
| Data processing, quantification and analysis | DM, WS |  | Comparing constant frame rate data with ATS by quantifying different performance metrics.
Application: bacterial division | Test detection performance and parameters | WS |  | Test whether existing event detection framework works on bacterial data. Tune adaptation response parameters to this new context. | If doesn't work will have to add additional tasks including generating a training dataset.
| Acquire adaptive data | WS, DM |  | Willi in charge of bacterial division, Dora shadowing | If I'm still here when we get to try this.
| Acquire non-adaptive data | WS, DM |  | Willi in charge of bacterial division, Dora shadowing. Data with constant frame rates: same as min and max used in ATS. | If I'm still here when we get to try this.
| Sample preparation |  |  | Producing samples. | Get help from Hélène or Chen.
Manuscript | Manuscript - original draft preparation | DM, SM | WS | Writing outline, original draft.
| Manuscript - review and editing | WS, JG, MW |  | Editing and reviewing manusript draft.
| Figure preparation | DM, WS |  | Self explanatory

## 18.02.2020 copy
Project contributors (past, present): | Task status color code: | Main contributors: | Other contributors:
Suliana Manley (SM) | Completed | Execute, direct involvement | Advise, brainstorm, etc.
Dora Mahecic (DM) | Ongoing
Willi Stepp (WS) | Not yet started
Sheda Ben Nejma (SBN)
Santiago Nicolas Rodriguez Alvarez (SNRA)
Aim | Task | Main contributor(s) | Other contributor(s) | Description | Comments
Supervision and management | Conceptualization |  |  | Development of basic idea and storyline.
| Funding acquisition |  |  | ?
| Supervision |  |  | SM, WS and SBN overall supervision
| Project administration |  |  | Task distribution, keeping track of data, planning, taking care of this sheet, etc.
Event detection framework | Preliminary event detection | DM |  | Calculate readout from acquired images on the fly (here using intensity of molecular marker), to adjust temporal resolution.
| Develop automatic labelling procedure | DM |  | Identifying a method to automatically label mitochondrial constrictions. Conceptualized and implemented using Hessian filtering.
| Generate training dataset | DM |  | Large scale processing of data using Hessian filtering data labeling strategy and manually editing said dataset to create the optimal training dataset.
| Ground Truth preprocessing |  | SNRA | Modify the preliminary detected events to improve network performance by replacing them with disk-shaped gaussian fissions. Distance Transform Watershed is used for automatic labelling of touching fissions.
| Data augmentation |  | SNRA | Expand training dataset by applying a set of transformations to both input and output data. The latter data is adapted with the same protocol as in the GT preprocessing stage.
| Temporal filter |  | SNRA | Detect irrelevant frames based on their mean probability of including events of interest. This temporal signal is smoothed by using a median filter, so that noise in the GT is removed, which allows obtaining a clear binary signal.
| Build and train neural network | DM | SNRA | Creating the neural network and training using labelled dataset.
| Characterize performance and optimize network parameters | DM | SNRA | Optimizing network parameters and quantifying performance based on the probability map outputs.
Manuscript | Manuscript - original draft preparation
Manuscript - review and editing
Figure preparation

## Sheet1
Project contributors (past, present): | Task status color code: | Main contributors: | Other contributors:
Suliana Manley (SM) | Completed | Execute, direct involvement | Advise, brainstorm, etc.
Dora Mahecic (DM) | Ongoing
Juliette Griffié (JG) | Not yet started
Khalid Ibrahim (KI)
Willi Stepp (WS)
Hélène Perreten Lambert (HPL)
Florent Wenger (FW)
Martin Weigert (MW)
Aim | Task | Main contributor(s) | Other contributor(s) | Description | Comments
Supervision and management | Conceptualization | SM, DM | JG | Development of basic idea and storyline.
| Funding acquisition | SM |  | ?
| Supervision | SM, DM |  | SM overall supervision, DM training and integrating new project members.
| Project administration | SM, DM |  | Task distribution, keeping track of data, planning, taking care of this sheet, etc.
Smart acquisition framework | Preliminary iSIM hardware and software work | DM |  | Putting in place the hardware and software for iSIM operation. Software easily modifiable and user friendly.
| Develop framework for continuous and adjustable iSIM acquisition | DM |  | Modifying existing iSIM acquisition controls to allow for continuously adjustable iSIM acquisition. Conceptualization of how to best implement adjustable temporal resolution.
| Integrate event detection network into smart framework | WS | DM, MW, FW | Connect smart iSIM controls with the network by organising the data flow between MicroManager, MATLAB and the network python scripts. Conceptualization done by Willi & Dora, execution by Willi.
Event detection framework | Preliminary event detection | DM | SM | Calculate readout from acquired images on the fly (here using intensity of molecular marker), to adjust temporal resolution.
| Develop automatic labelling procedure | DM | JG, MW, KI | Identifying a method to automatically label mitochondrial constrictions. Conceptualized and implemented using Hessian filtering. Previous attempts by KI did not appear successful.
| Generate training dataset | DM |  | Large scale processing of data using Hessian filtering data labeling strategy and manually editing said dataset to create the optimal training dataset.
| Build and train neural network | DM | MW | Creating the neural network and training using labelled dataset.
| Characterize performance and optimize network parameters | DM |  | Optimizing network parameters and quantifying performance based on the probability map outputs.
Simulation platform | Develop simulation platform using synthetic data | DM | JG | Testing different strategies using simulated readouts and quantifying the benefit of ATS.
| Develop simulation platform using real data | WS | DM, JG | Adapting GUI to read frame based on metric computed from previously read frame. | Not crucial at this point and not sure it will address what I hope, but worth keeping in mind. I think the current GUI from Willi could be easily adapted for this purpose.
Application: mitochondrial division | Acquire adaptive data | DM, WS |  | Dora in charge of mitochondrial division, Willi shadowing
| Acquire non-adaptive data | DM |  | Data with constant frame rate: same as min and max used in ATS.
| Optimize decision parameters | DM, WS |  | Choosing trigger for adaptation response. Optimising behaviour to minimise noise and maximise event recognition. | Eventually might be useful to use simulation platform for this.
| Sample preparation | HPL, DM |  | Finding best labeling strategy. Producing samples
| Data processing, quantification and analysis | DM, WS |  | Comparing constant frame rate data with ATS by quantifying different performance metrics.
Application: bacterial division | Test detection performance and parameters | WS |  | Test whether existing event detection framework works on bacterial data. Tune adaptation response parameters to this new context. | If doesn't work will have to add additional tasks including generating a training dataset.
| Acquire adaptive data | WS, DM |  | Willi in charge of bacterial division, Dora shadowing | If I'm still here when we get to try this.
| Acquire non-adaptive data | WS, DM |  | Willi in charge of bacterial division, Dora shadowing. Data with constant frame rates: same as min and max used in ATS. | If I'm still here when we get to try this.
| Sample preparation |  | CZ | Producing samples. | Get help from Hélène or Chen.
Manuscript | Manuscript - original draft preparation | DM, SM | WS | Writing outline, original draft.
| Manuscript - review and editing | WS, JG, MW |  | Editing and reviewing manusript draft.
| Figure preparation | DM, WS |  | Self explanatory